## Gantt Chart
Hostel Management System — Project Gantt Chart
CSE 220 – Principles of Software Engineering ¦ HMS Case Study
Project Lead: | Shiva Bhattarai
Project Start: | Mon, 8/17/2026 | [5 empty] | ▼
Today: | Wed, 8/19/2026
[5 empty] | Aug 17, 2026 | [6 empty] | Aug 24, 2026 | [6 empty] | Aug 31, 2026 | [6 empty] | Sep 7, 2026 | [6 empty] | Sep 14, 2026
[5 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Task | Assigned To | Progress | Start | End | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Sprint 1 – Development
US-01: Apply for Hostel Room | Shiva Bhattarai | 50% | 8/17/26 | 8/21/26 | bar: Aug 17, 2026 M to Aug 17, 2026 S
US-09: Secure Role-Based Login | Niraj Gautam | 40% | 8/17/26 | 8/22/26 | bar: Aug 17, 2026 M to Aug 17, 2026 S
US-02: Allocate Rooms to Students | Ronak Chand | 20% | 8/18/26 | 8/23/26 | bar: Aug 17, 2026 T to Aug 17, 2026 S
US-03: View Room and Roommate Details | Shiva Bhattarai | 0% | 8/19/26 | 8/24/26 | bar: Aug 17, 2026 W to Aug 24, 2026 M
US-04: Mark Daily Hostel Attendance | Ronak Chand | 0% | 8/20/26 | 8/26/26 | bar: Aug 17, 2026 T to Aug 24, 2026 W
Sprint 1 – Testing
Unit Testing (Login, Rooms, Attendance) | Niraj Gautam | 0% | 8/22/26 | 8/26/26 | bar: Aug 17, 2026 S to Aug 24, 2026 W
Integration Testing (App→Allocation, Attendance→Alert) | Niraj Gautam | 0% | 8/24/26 | 8/27/26 | bar: Aug 17, 2026 S to Aug 24, 2026 T
System Testing (End-to-end, Lockout, Performance) | Niraj Gautam | 0% | 8/23/26 | 8/28/26 | bar: Aug 17, 2026 S to Aug 24, 2026 S
UAT (Student, Warden, Login Access) | Shiva Bhattarai & Ronak Chand | 0% | 8/28/26 | 8/29/26 | bar: Aug 17, 2026 S to Aug 17, 2026 S; Aug 24, 2026 F to Aug 24, 2026 S
Sprint 2 – Development
US-05: Submit Maintenance Complaints | Shiva Bhattarai | 0% | 8/31/26 | 9/4/26 | bar: Aug 17, 2026 S to Aug 17, 2026 S; Aug 24, 2026 S to Aug 31, 2026 S
US-07: Pay Hostel Fees Online | Shiva Bhattarai | 0% | 8/31/26 | 9/9/26 | bar: Aug 17, 2026 S to Aug 17, 2026 S; Aug 24, 2026 S to Sep 7, 2026 W
US-06: Track and Update Complaint Status | Ronak Chand | 0% | 9/1/26 | 9/6/26 | bar: Aug 17, 2026 S to Aug 17, 2026 S; Aug 31, 2026 T to Aug 31, 2026 S
US-08: Parent Notifications on Attendance/Fees | Niraj Gautam | 0% | 9/3/26 | 9/8/26 | bar: Aug 17, 2026 S to Aug 17, 2026 S; Aug 31, 2026 T to Sep 7, 2026 T
US-10: Generate Occupancy and Revenue Reports | Niraj Gautam | 0% | 9/4/26 | 9/12/26 | bar: Aug 17, 2026 S to Aug 17, 2026 S; Aug 31, 2026 F to Sep 7, 2026 S
Sprint 2 – Testing
Unit Testing (Fees) | Niraj Gautam | 0% | 9/9/26 | 9/9/26 | bar: Aug 17, 2026 S to Aug 17, 2026 S; Sep 7, 2026 W
Integration Testing (Complaints, Fees, Reports) | Niraj Gautam | 0% | 9/7/26 | 9/13/26 | bar: Aug 17, 2026 S to Aug 17, 2026 S; Aug 31, 2026 S to Sep 7, 2026 S
System Testing (Complaint Reopen, Report Totals) | Niraj Gautam | 0% | 9/8/26 | 9/14/26 | bar: Aug 17, 2026 S to Aug 17, 2026 S; Sep 7, 2026 T to Sep 14, 2026 M
UAT (Complaints, Fees, Notifications, Reports) | Shiva Bhattarai & Ronak Chand | 0% | 9/9/26 | 9/15/26 | bar: Aug 17, 2026 S to Aug 17, 2026 S; Sep 7, 2026 W to Sep 14, 2026 T
Legend
Sprint 1 – Development (dark = completed, light = remaining)
Sprint 1 – Testing (dark = completed, light = remaining)
Sprint 2 – Development (dark = completed, light = remaining)
Sprint 2 – Testing (dark = completed, light = remaining)
Today (8/19/2026)